## Slide 1: 2025/26 Operating Plan
Community Care of West Niagara

## Slide 2: Vision
“Growing our Community Beyond Hunger.”

## Slide 3: Mission
“We exist to provide essential services and support to families and individuals in Lincoln facing economic hardship. Our goal is to bridge the journey of our vulnerable as they strive to restore balance and self-sufficiency.”

## Slide 4: Core Values and Guiding Principles
Deliver impact through compassionate service
Embrace and drive change with integrity
Be relevant and respectful
Foster community resilience and nurture hope

## Slide 5: Strategic Pillars and Key Strategic Outcomes 2025-2029
Enhancing quality of life for our clients:
Served as a founding partner, driving FEED Niagara toward successful independence
Expanded storage capacity and reach of food services
Contributed meaningfully to the development of affordable housing in the Town of Lincoln
Strengthening our curbside credibility:
Obtained and maintained full accreditation
Increased brand recognition as a leading social services agency in West Niagara
Ensuring our long-term sustainability:
Established a successful program for Legacy Giving and Major Gifts

## Slide 6: 2025/26 Operating Plan: KSO #1 A founding partner driving FEED Niagara toward successful independence
 | Initiative | Owner | Contributor | Deadline | Status | Notes
1-A | Complete ratification of MOU for FEED Niagara members | Emma | Carole | July 15/25 |  | 
1-B | Hire and onboard new FEED Niagara manager | Carole | Emma | October 31/25 |  | 
1-C | Document critical path for FEED Niagara independence | Carole | F/N Manager | January 31/26 |  | 
1-D | Fulfill requirements of 3 FEED Niagara grants | Emma | Nicole Carole | January 31/26 |  | 
1-E | Identify and secure physical space for FEED Niagara | Carole | F/N Manager | December 31/25 |  | In consultation with FN Consortium

## Slide 7: 2025/26 Operating Plan: KSO #2 Expanded storage capacity and reach of food services
 | Initiative | Owner | Contributor | Deadline | Status | Notes
2-A | Complete staff-level assessment of BDSS and other off-site alternatives, with recommendations to the Board | Nicole | Carole | September 24/25 |  | 
2-B | Complete food capacity analysis | Nicole | Carole | November 1/25 |  | 
2-C | Publish food recovery (i.e. foodrescue.ca) analysis and report | Lynda |  | November 1/25 |  | 
2-D | Create and finalize a plan to re-establish ongoing service in Vineland | Emma | Carole F/N Manager | November 1/25 |  | Includes developing KPIs for Vineland operations

## Slide 8: 2025/26 Operating Plan: KSO #3 A meaningful contributor to the development of affordable housing in the Town of Lincoln
 | Initiative | Owner | Contributor | Deadline | Status | Notes
3-A | Evaluate succession opportunity on Mayor’s Housing Select Committee | Carole | Dora | October 31/25 |  | Attend Town COW meeting on July 21 2025
3-B | Create housing stakeholder engagement plan | Dora | Nicole | October 22/25 |  | 

## Slide 9: 2025/26 Operating Plan: KSO #4 Obtained and maintained full accreditation
 | Initiative | Owner | Contributor | Deadline | Status | Notes
4-A | Conduct orientation session with staff regarding accreditation standards and auditing tool | Carole |  | October 31/25 |  | 
4-B | Complete Board review of new and/or revised policies in support of accreditation | Carole | Emma | January 2026 |  | 
4-C | Complete accreditation with Food Banks Canada Standards of Excellence | Carole |  | March 2026 |  | 

## Slide 10: 2025/26 Operating Plan: KSO #5 Increased brand recognition as a leading social services agency in West Niagara
 | Initiative | Owner | Contributor | Deadline | Status | Notes
5-A | Conduct website review | Emma |  | October 15/25 |  | 
5-B | Complete and report to Board on assessment of current marketing strategy and activities | Emma | Carole | October 15/25 |  | Carole to present findings to BOD
5-C | Conduct Stakeholder Survey re Brand Recognition and Key Messages | Emma |  | January 2026 |  | 
5-D | Engage outside consultant to support development of new marketing strategy | Emma | Carole | December 31/25 |  | 
5-E | Develop DRAFT marketing strategy for CCWN | Emma | Carole | April 2026 |  | Carole to present draft to BOD

## Slide 11: 2025/26 Operating Plan: KSO #6 Established a successful program for Legacy Giving and Major Gifts
 | Initiative | Owner | Contributor | Deadline | Status | Notes
6-A | Conduct analysis of donor relationships, historical major gifts, and potential new donors | Lynda | Carole | November 1 2026 |  | 
6-B | Include in ED reports regular updates on research regarding legacy giving program development and best practices | Carole | Lynda | November 1 2026 |  | 
6-C | Develop framework for Donor Recognition Program | Lynda | Carole | February 2026 |  | Identify elements in place and gaps to focus on; polices and resources needed
6-D | Develop framework for Legacy Giving and Major Gifts program | Lynda | Carole | March 2026 |  | Identify elements in place and gaps to focus on; polices and resources needed
6-E | Develop plan for 60th anniversary supporter event | Lynda |  | June 2026 |  | 

## Slide 12: 2025/26 Operating Plan: Corporate Initiatives
 | Initiative | Owner | Contributor | Deadline | Status | Notes
1-A | Cross-train Dora on Link2Feed data extraction and reporting | Nicole | Dora | July 31/25 |  | Attend learning sessions ie: webinars
1-B | Cross-train Nicole on food data entry (i.e. foodrescue.ca) | Lynda | Nicole | August 15/25 |  | 
1-C | Complete assessment of donor management system utilization, with recommendations | Lynda | Emma | October 31/25 |  | 
1-D | Complete Human Resources assessment in support of new strategic plan | Carole |  | November 30/25 |  | Review job descriptions and liaise with HR committee
1-E | Conduct Technology Audit and Needs Assessment | Nicole | Carole | January 2026 |  | Review types of audits, survey FN members and identify priorities
1-F | Assess volunteer recruitment and integration programs and processes | Nicole |  | January 2026 |  | 

## Slide 13: Operational Performance Targets (In development) As at July 01, 2025
Food security rate:
Client service rate:
Reduced service levels rate:
Turn-aways:
Food diversity score:
Food donations:
Monetary donations:
Total volunteers:

## Slide 14: Operational Performance Targets (In development)
Total clients:
New partnerships (past quarter):
HIFIS KPIs